## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Willie's Cycles | [6 empty] | Completed | 1
| Team Members: | Ethan Coggin, John Boggan, Dillon Clary, Sean Walker, Shernovius Bennett | [6 empty] | Discarded | 2
| Date: | 2015-02-23 | Cycle: | 1 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | "Everybody needs a little Willie's" - A mobile application with which users can search for, bid on, and purchase parts from Willie's Cycles. | [6 empty] | In Review
Unstarted
| Cycle Intent: | Establish the underlying structure and direction necessary for the mobile aspect of development in cycles 2 and 3. Complete the web service to allow interaction with the current inventory.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Populate list of parts from the inventory database |  | 1 | 15 | 15 | Adversarial | 8.75 | 8.75
2 | Search for parts by part type, make, model, etc. |  | 1 | 25 | 25 | Adversarial | 4 | 4
3 | Android App – Display list of parts that satisfy search conditions |  | 1 | 10 | 10 | Unstarted | 0 | 0
4 | iOS App – Display list of parts that satisfy search conditions |  | 1 | 10 | 10 | Unstarted | 0 | 0
5 | Login with PayPal |  | 2 | 15 | 5 | Unstarted | 0 | 0
|  |  | Planned Total | 75 | 65 | Actual Total | 12.75 | 12.75

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Willie's Cycles
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Ethan Coggin | 2; 3; 5 | 2; 5 | 4 | 2 | 24 |  |  | 1.25 | 3.25 |  |  |  |  | 1.25 | 3.25
| John Boggan | 1; 2; 4; 5 | 1; 5 | 3 | 2 | 24 |  |  | 1 | 8.5 |  |  | 2.75 | 7.75 | 3.75 | 16.25
| Dillon Clary | 1; 3; 4 | 1; 3; 4 |  | 2 | 24 |  |  | 4.5 | 4.5 |  | 2 |  | 2 | 4.5 | 8.5
| Sean Walker | 1; 2 | 2 | 5 | 2 | 24 |  | 1.5 | 1.5 | 1.5 |  |  | 1 | 1 | 2.5 | 4
| Shernovius Bennett | 1; 2 | 1; 2 |  | 2 | 24 |  | 1.5 |  | 2 | 2 | 5 | 2 | 2 | 4 | 10.5
[5 empty] | Totals | 120 | 0 | 3 | 8.25 | 19.75 | 2 | 7 | 5.75 | 12.75 | 16 | 42.5
Planned Product Hours < 80% Planned Team Hours.
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| Web server and MS Access database are now successfully communicating, previously we were not able to access remotely. We've done some preliminary wireframing for the iOS and Android apps. We have written some of the database queries for the Web API. We now have Xamarin licenses, so we have the tools necessary for our Android and iOS app development. | [6 empty] | Finish setting up the Web API for parts searching. Have one screen of the Android and iOS apps done where the user can search for a part (through the Web API) and then populate a list of parts returned from that search.
| Obstacles encountered since last status report: | [6 empty] | Notes:
| Willie's Cycles is storing customer information in a non-secure manner that may present some security and legality issues. We all had busy schedules this week, so we were not able to get much work done this week. | [6 empty] | We modified our Status Report based on Dr. Chapman's comments, so our Page 1 and Planned Hours have been adjusted.
Risks facing the project:
We are still waiting for their third party developer to move Willie's Cycles' current file-based inventory system over to the new system that will utilize Microsoft Access. Also establishing the software on the local server at Willie's. The firewall configuration will have to be duplicated on their server.

## Member 1 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Ethan Coggin
Week Ending: |  | 2015-02-23
Cycle: |  | Cycle 1
Team Member Work Summary
Monday | Tuesday | Task(s) performed:
Date: | 2015-02-17 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2015-02-18 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-02-19 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-02-20 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-02-21 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | Watched Pierce's video on updating the server. Downloaded Visual Studio on my new computer.
Date: | 2015-02-22 | Result: | Visual Studio downloaded and set up.
Hours Worked: | 0.5 | Problems encountered: | None
Day: | Monday | Task(s) performed: | Set up Status Report for this week so that each team member could enter their information. Modified Status Report based on Dr. Chapman's comments.
Date: | 2015-02-23 | Result: | Status Report set up and hosted on Google Sheets. Created a template for future Status Reports.
Hours Worked: | 0.75 | Problems encountered: | None

## Member 2 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | John Boggan
Week Ending: |  | 2015-02-23
Cycle: |  | Cycle 1
Team Member Work Summary
Monday | Tuesday | Task(s) performed: | Senior Design Windows Setup
Date: | 2015-02-17 | Result: | Succesfully installed necessary software for working with our Android app, as well as our web service.
Hours Worked: | 1 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Server to Access Communication
Date: | 2015-02-18 | Result: | Successfully have our web server and access database communication. Before, we got a permissions exception when trying to access remotely. Only step now is to refactor database logic!
Hours Worked: | 2.75 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-02-19 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-02-20 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-02-21 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-02-22 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2015-02-23 | Result:
Hours Worked: | 0 | Problems encountered:

## Member 3 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Dillon Clary
Week Ending: |  | 2015-02-23
Cycle: |  | Cycle 1
Team Member Work Summary
Monday | Tuesday | Task(s) performed:
Date: | 2015-02-17 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Wireframing the Android and iOS apps. Updated User Stories.
Date: | 2015-02-18 | Result: | User Stories finalized.
Hours Worked: | 1 | Problems encountered: | None
Day: | Thursday | Task(s) performed:
Date: | 2015-02-19 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-02-20 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-02-21 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-02-22 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed: | Wireframes for iOS and Andriod.
Date: | 2015-02-23 | Result: | Wireframes finished.
Hours Worked: | 3.5 | Problems encountered:

## Member 4 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Sean Walker
Week Ending: |  | 2015-02-23
Cycle: |  | Cycle 1
Team Member Work Summary
Monday | Tuesday | Task(s) performed:
Date: | 2015-02-17 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Process on upcoming tasks
Date: | 2015-02-18 | Result: | Discussed Payment methods to use and routes to take (Paypal login) Discussed testing for current build
Hours Worked: | 1.5 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-02-19 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-02-20 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed: | Started writing some test cases
Date: | 2015-02-21 | Result: | No tests written, but better understanding of what needs to be done and what direction to go
Hours Worked: | 1 | Problems encountered: | New to Web API's and C#. Visual Studio on my local machine wouldn't build project as a Web API to test
Day: | Sunday | Task(s) performed:
Date: | 2015-02-22 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2015-02-23 | Result:
Hours Worked: | 0 | Problems encountered:

## Member 5 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Shernovius Bennett
Week Ending: |  | 2015-02-23
Cycle: |  | Cycle 1
Team Member Work Summary
Monday | Tuesday | Task(s) performed: | Discuss Pending Security Issues with Willie's Employees
Date: | 2015-02-17 | Result: | Determine to simply include disclosure agreeement
Hours Worked: | 2 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Explore query options
Date: | 2015-02-18 | Result: | Determine Query statement to search database
Hours Worked: | 2 | Problems encountered: | Finding access query builder
Day: | Thursday | Task(s) performed:
Date: | 2015-02-19 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-02-20 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-02-21 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-02-22 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2015-02-23 | Result:
Hours Worked: | 0 | Problems encountered: