## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Willie's Cycles | [6 empty] | Completed | 1
| Team Members: | Ethan Coggin, John Boggan, Dillon Clary, Sean Walker, Shernovius Bennett | [6 empty] | Discarded | 2
| Date: | 2015-03-04 | Cycle: | 1 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | "Everybody needs a little Willie's" - A mobile application with which users can search for and purchase parts from Willie's Cycles. | [6 empty] | In Review
Unstarted
| Cycle Intent: | Establish the underlying structure and direction necessary for the mobile aspect of development in cycles 2 and 3. Complete the web service to allow interaction with the current inventory.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Search for Parts |  | 1 | 40 | 40 | Adversarial | 18.25 | 18.25
2 | Select a Make |  | 2 | 5 | 2 | Collaboration | 1.5 | 1.5
3 | Select a Year |  | 2 | 5 | 2 | Collaboration | 1.5 | 1.5
4 | Select a Part Name |  | 2 | 5 | 2 | Collaboration | 1.5 | 1.5
5 | Change the Search Year |  | 2 | 5 | 0 | Unstarted | 0 | 0
6 | Clear the Search |  | 2 | 5 | 0 | Unstarted | 0 | 0
7 | Purchase a Part |  | 2 | 20 | 0 | Unstarted | 0 | 0
8 | Pay for a Part with PayPal |  | 2 | 20 | 0 | Collaboration | 2.5 | 2.5
9 | Request Additional Information About a Part |  | 2 | 10 | 0 | Unstarted | 0 | 0
10 | View About Us Screen |  | 3 | 5 | 0 | Unstarted | 0 | 0
11 | DISCARDED: Login with Paypal |  | 2 | 15 | 5 | Discarded | 0 | 0
|  |  | Planned Total | 120 | 46 | Actual Total | 25.25 | 25.25

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Willie's Cycles
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Ethan Coggin | 1; 7; 8 | 1; 7; 8 | 2; 3; 4 | 1; 7; 8 | 24 | 0.5 | 0.5 | 17.25 | 20.5 |  |  | 2 | 2 | 19.75 | 23
| John Boggan | 1; 2; 3; 4; 7; 8 | 1; 2; 3; 4; 7; 8 | 1; 2; 3; 4 | 1; 7; 8 | 24 |  |  | 4.5 | 13 |  |  | 2.5 | 10.25 | 7 | 23.25
| Dillon Clary | 1; 2; 3; 4; 7; 8 | 1 | 7; 8 | 1; 7; 8 | 24 |  |  | 8.5 | 13 |  | 2 |  | 2 | 8.5 | 17
| Sean Walker | 1; 2; 3; 4; 7; 8 | 1; 2; 3; 4 | 1; 2; 3; 4; 7; 8 | 1; 7; 8 | 24 |  | 1.5 | 9.5 | 11 |  |  | 5.5 | 6.5 | 15 | 19
| Shernovius Bennett | 1; 7; 8 | 1; 7; 8 | 1 | 1; 7; 8 | 24 | 0.5 | 2 | 13 | 15 | 2 | 7 | 2.5 | 4.5 | 18 | 28.5
[5 empty] | Totals | 120 | 1 | 4 | 52.75 | 72.5 | 2 | 9 | 12.5 | 25.25 | 68.25 | 110.75
Planned Product Hours < 80% Planned Team Hours.
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| WebAPI is now returning a list of Parts with all necessary fields. We can now use the Web API to Query the database and search by Year, Make, and Model. We've added XML Documentation to the Web API web page. We have completed our UI wireframe mockups. The apps are now successfully populating a list of items from the database based upon search parameters that are passed to the API. | [6 empty] | Complete the UI design from the wireframes mockups. Incorproate the new UI design into both apps to improve the user experience.
| Obstacles encountered since last status report: | [6 empty] | Notes:
| For some reason, the XML document used to populate the Web API documentation was removed from the project (even though it was still being generated properly) which caused the Web API to stop functioning. Upon further research we realized that using PayPal to login would not work for what we were trying to use it for, so we've had to adjust our approach accordingly. | [6 empty] | We updated the User Stories on Page 1 and 2 of the Status Report to match our finalized User Stories.
Risks facing the project:
We are still waiting for their third party developer to move Willie's Cycles' current file-based inventory system over to the new system that will utilize Microsoft Access. Also establishing the software on the local server at Willie's. The firewall configuration will have to be duplicated on their server.

## Member 1 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Ethan Coggin
Week Ending: |  | 2015-03-04
Cycle: |  | Cycle 1
Team Member Work Summary
Monday | Tuesday | Task(s) performed: | Working on Web API database accessing. Adding Web API XML documentation. Prepped Status Report for this week.
Date: | 2015-02-24 | Result: | Encapsulated Database interactions in a separate class for ease of testing. Web API now returns all Part information and list of parts. Can now query by year, make, and part name. XML documentation now appears on WebAPI webpage. Status Report prepped and on Google Sheets for this week.
Hours Worked: | 2.5 | Problems encountered: | Prices appear to be doubles, but they are returned from the database as strings. XML documentation will not appear without uncommenting a specific line in the project settings.
Day: | Wednesday | Task(s) performed:
Date: | 2015-02-25 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-02-26 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-02-27 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-02-28 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | Corrected Parts query syntax. Fixed issue with XmlDocument.xml being removed from the project. Working on Cycle Report. Working on Presentation.
Date: | 2015-03-01 | Result: | Parts query is now working.
Hours Worked: | 2.75 | Problems encountered: | For some reason the XmlDocument.xml used for creating the documentation on the WebAPI website wasn't being included in the project (even though it was being created), so the WebAPi wasn't working. I'm not sure what caused this issue as it was working previously.
Day: | Monday | Task(s) performed: | Working on presentation.
Date: | 2015-03-02 | Result: | Presentation completed.
Hours Worked: | 4 | Problems encountered: | None
Day: | Tuesday | Task(s) performed: | Working on Cycle Report.
Date: | 2015-03-03 | Result: | Progress made on Cycle Report.
Hours Worked: | 2 | Problems encountered: | None
Day: | Wednesday | Task(s) performed: | Working on Cycle Report. Updating Status Report with finalized User Stories.
Date: | 2015-03-04 | Result: | Cycle report completet. Page 1 and 2 of Status Report updated with new finalized User Stories.
Hours Worked: | 8.5 | Problems encountered: | None

## Member 2 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | John Boggan
Week Ending: |  | 2015-03-04
Cycle: |  | Cycle 1
Team Member Work Summary
Monday | Tuesday | Task(s) performed:
Date: | 2015-02-24 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2015-02-25 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-02-26 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-02-27 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-02-28 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | Added search UI to Willie's iOS client.
Date: | 2015-03-01 | Result: | Users can now query using part name, make, and year on the iOS client, and a table will display the results.
Hours Worked: | 2.5 | Problems encountered:
Day: | Monday | Task(s) performed: | Presentation prep. Pull together slides and practice presentation.
Date: | 2015-03-02 | Result: | Presentation completed. Dr. Chapman said one of the best in the class!
Hours Worked: | 3 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2015-03-03 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Working on cycle report
Date: | 2015-03-04 | Result: | Updated Testing section
Hours Worked: | 1.5 | Problems encountered:

## Member 3 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Dillon Clary
Week Ending: |  | 2015-03-04
Cycle: |  | Cycle 1
Team Member Work Summary
Monday | Tuesday | Task(s) performed: | Changed User Stories
Date: | 2015-02-24 | Result: | Number of user stories reduced, wireframes affected.
Hours Worked: | 1 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2015-02-25 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-02-26 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-02-27 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-02-28 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | Working on wireframe mockups
Date: | 2015-03-01 | Result: | Wireframe mockups complete
Hours Worked: | 3.5 | Problems encountered:
Day: | Monday | Task(s) performed: | Working on presentation
Date: | 2015-03-02 | Result: | Presentation done
Hours Worked: | 4 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2015-03-03 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2015-03-04 | Result:
Hours Worked: | 0 | Problems encountered:

## Member 4 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Sean Walker
Week Ending: |  | 2015-03-04
Cycle: |  | Cycle 1
Team Member Work Summary
Monday | Tuesday | Task(s) performed:
Date: | 2015-02-24 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2015-02-25 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-02-26 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-02-27 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-02-28 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | Worked on search functionality for Android application
Date: | 2015-03-01 | Result: | Created MainActivity, which holds a simple basic unpolished UI for performing searched
Hours Worked: | 3 | Problems encountered: | Niether computers in the Senior Design room have the SDK's for Android. Had to work from personal machine, which required registering of Xamarin trial license.
Day: | Monday | Task(s) performed: | Worked more on Android application
Date: | 2015-03-02 | Result: | Finshed up populating spinners for search options and using parameters from spinners to perfmor searches. Met with group and created presentation for end of Cycle 1
Hours Worked: | 6 | Problems encountered: | Not skilled in C#, had to figure out some issues along the way
Day: | Tuesday | Task(s) performed:
Date: | 2015-03-03 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Worked on end of Cycle report
Date: | 2015-03-04 | Result: | Filled in design documentation, source code, and gantt chart
Hours Worked: | 6 | Problems encountered:

## Member 5 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Shernovius Bennett
Week Ending: |  | 2015-03-04
Cycle: |  | Cycle 1
Team Member Work Summary
Monday | Tuesday | Task(s) performed: | Meeting with Dan. Group meeting to set goals for the week
Date: | 2015-02-24 | Result: | Discussed credit card issue
Hours Worked: | 6 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2015-02-25 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | Examine C# Xamarin SDK for PayPal
Date: | 2015-02-26 | Result: | Determine SDK doesn't work for both OS
Hours Worked: | 2.5 | Problems encountered: | SDK didn't work across platforms
Day: | Friday | Task(s) performed:
Date: | 2015-02-27 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-02-28 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | Group meeting to work on design presentation
Date: | 2015-03-01 | Result: | Design presentation
Hours Worked: | 3.5 | Problems encountered:
Day: | Monday | Task(s) performed: | Group meeting to work on design presentation
Date: | 2015-03-02 | Result: | Design presentation
Hours Worked: | 4 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2015-03-03 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Group meeting
Date: | 2015-03-04 | Result: | Cycle Report
Hours Worked: | 2 | Problems encountered: