## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Willie's Cycles | [6 empty] | Completed | 1
| Team Members: | Ethan Coggin, John Boggan, Dillon Clary, Sean Walker, Shernovius Bennett | [6 empty] | Discarded | 2
| Date: | 2015-03-09 | Cycle: | 2 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | "Everybody needs a little Willie's" - A mobile application with which users can search for and purchase parts from Willie's Cycles. | [6 empty] | In Review
Unstarted
| Cycle Intent: | Finalize and implement the design of the mobile application user interface. Enable the user to search for and purchase parts with the mobile application.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Search for Parts |  | 1 | 40 | 10 | Adversarial | 0 | 18.25
2 | Select a Make |  | 2 | 5 | 3 | Collaboration | 0 | 1.5
3 | Select a Year |  | 2 | 5 | 3 | Collaboration | 0 | 1.5
4 | Select a Part Name |  | 2 | 5 | 3 | Collaboration | 0 | 1.5
5 | Change the Search Year |  | 2 | 5 | 5 | Unstarted | 0 | 0
6 | Clear the Search |  | 2 | 5 | 5 | Unstarted | 0 | 0
7 | Purchase a Part |  | 2 | 20 | 20 | Unstarted | 0 | 0
8 | Pay for a Part with PayPal |  | 2 | 20 | 17.5 | Collaboration | 0 | 2.5
9 | Request Additional Information About a Part |  | 2 | 10 | 10 | Unstarted | 0 | 0
10 | View About Us Screen |  | 3 | 5 | 0 | Unstarted | 0 | 0
11 | DISCARDED: Login with Paypal |  | 2 | 15 | 5 | Discarded | 0 | 0
|  |  | Planned Total | 120 | 76.5 | Actual Total | 0 | 25.25

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Willie's Cycles
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Ethan Coggin | 1; 7; 8 | 1; 7; 8 | 2; 3; 4 | 1; 7; 8 | 30 |  |  | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.5
| John Boggan | 1; 2; 3; 4; 7; 8 | 1; 2; 3; 4; 7; 8 | 1; 2; 3; 4 | 1; 7; 8 | 30 | [8 empty] | 0 | 0
| Dillon Clary | 1; 2; 3; 4; 7; 8 | 1 | 7; 8 | 1; 7; 8 | 30 | [8 empty] | 0 | 0
| Sean Walker | 1; 2; 3; 4; 7; 8 | 1; 2; 3; 4 | 1; 2; 3; 4; 7; 8 | 1; 7; 8 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Shernovius Bennett | 1; 7; 8 | 1; 7; 8 | 1 | 1; 7; 8 | 30 | [8 empty] | 0 | 0
[5 empty] | Totals | 150 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5
Planned Product Hours < 80% Planned Team Hours.
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| Completed the Cycle Report and deliverables for Cycle 1. | [6 empty] | Complete the UI design from the wireframes mockups. Incorproate the new UI design into both apps to improve the user experience.
| Obstacles encountered since last status report: | [6 empty] | Notes:
| It took more time to complete the deliverables for Cycle 1 than anticipated, so some of our Cycle 2 time was spent working on Cycle 1. | [6 empty] | We added the extra days spent working on the Cycle 1 deliverables to the previous Status Report since they were actually for Cycle 1 rather than Cycle 2, so those days/hours are not included here.
Risks facing the project:
We are still waiting for their third party developer to move Willie's Cycles' current file-based inventory system over to the new system that will utilize Microsoft Access. Also establishing the software on the local server at Willie's. The firewall configuration will have to be duplicated on their server.

## Member 1 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Ethan Coggin
Week Ending: |  | 2015-03-09
Cycle: |  | Cycle 2
Team Member Work Summary
Monday | Thursday | Task(s) performed:
Date: | 2015-03-05 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-03-06 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-03-07 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-03-08 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed: | Preparing Status Report for this week
Date: | 2015-03-09 | Result: | Status Report prepared
Hours Worked: | 0.5 | Problems encountered: | None

## Member 2 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | John Boggan
Week Ending: |  | 2015-03-09
Cycle: |  | Cycle 2
Team Member Work Summary
Monday | Thursday | Task(s) performed:
Date: | 2015-03-05 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-03-06 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-03-07 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-03-08 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2015-03-09 | Result:
Hours Worked: | 0 | Problems encountered:

## Member 3 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Dillon Clary
Week Ending: |  | 2015-03-09
Cycle: |  | Cycle 2
Team Member Work Summary
Monday | Thursday | Task(s) performed:
Date: | 2015-03-05 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-03-06 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-03-07 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-03-08 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2015-03-09 | Result:
Hours Worked: | 0 | Problems encountered:
Day:
Date:
Hours Worked:
Day:
Date:
Hours Worked:
Day:
Date:
Hours Worked:
Day:
Date:
Hours Worked:

## Member 4 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Sean Walker
Week Ending: |  | 2015-03-09
Cycle: |  | Cycle 2
Team Member Work Summary
Monday | Thursday | Task(s) performed:
Date: | 2015-03-05 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-03-06 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-03-07 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-03-08 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2015-03-09 | Result:
Hours Worked: | 0 | Problems encountered:
Day:
Date:
Hours Worked:
Day:
Date:
Hours Worked:
Day:
Date:
Hours Worked:
Day:
Date:
Hours Worked:

## Member 5 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Shernovius Bennett
Week Ending: |  | 2015-03-09
Cycle: |  | Cycle 2
Team Member Work Summary
Monday | Thursday | Task(s) performed:
Date: | 2015-03-05 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-03-06 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-03-07 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-03-08 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2015-03-09 | Result:
Hours Worked: | 0 | Problems encountered:
Day:
Date:
Hours Worked:
Day:
Date:
Hours Worked:
Day:
Date:
Hours Worked:
Day:
Date:
Hours Worked: