## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Willie's Cycles | [6 empty] | Completed | 1
| Team Members: | Ethan Coggin, John Boggan, Dillon Clary, Sean Walker, Shernovius Bennett | [6 empty] | Discarded | 2
| Date: | 2015-03-16 | Cycle: | 2 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | "Everybody needs a little Willie's" - A mobile application with which users can search for and purchase parts from Willie's Cycles. | [6 empty] | In Review
Unstarted
| Cycle Intent: | Finalize and implement the design of the mobile application user interface. Enable the user to search for and purchase parts with the mobile application.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Search for Parts |  | 1 | 40 | 10 | Adversarial | 4 | 23.25
2 | Select a Make |  | 2 | 5 | 3 | Adversarial | 1.5 | 3
3 | Select a Year |  | 2 | 5 | 3 | Adversarial | 1.5 | 3
4 | Select a Part Name |  | 2 | 5 | 3 | Adversarial | 1.5 | 3
5 | Change the Search Year |  | 2 | 5 | 5 | Unstarted | 0 | 0
6 | Clear the Search |  | 2 | 5 | 5 | Collaboration | 0.5 | 0.5
7 | Purchase a Part |  | 2 | 20 | 20 | Unstarted | 0 | 0
8 | Pay for a Part with PayPal |  | 2 | 20 | 17.5 | Collaboration | 3.5 | 6
9 | Request Additional Information About a Part |  | 2 | 10 | 10 | Unstarted | 0 | 0
10 | View About Us Screen |  | 3 | 5 | 0 | Unstarted | 0 | 0
11 | DISCARDED: Login with Paypal |  | 2 | 15 | 5 | Discarded | 0 | 0
|  |  | Planned Total | 120 | 76.5 | Actual Total | 12.5 | 38.75

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Willie's Cycles
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Ethan Coggin | 1; 5; 6; 7; 8 | 1; 5; 6; 7; 8 | 2; 3; 4 | 1; 7; 8 | 30 | 0 | 0 | 4 | 4.5 | 0 | 0 | 1.5 | 1.5 | 5.5 | 6
| John Boggan | 1; 2; 3; 4; 6; 7; 8 | 1; 2; 3; 4; 7; 8 | 1; 2; 3; 4; 6 | 1; 7; 8 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5 | 5.5 | 5.5 | 5.5
| Dillon Clary | 1; 2; 3; 4; 5; 6; 7; 8 | 1; 5; 6 | 7; 8 | 1; 7; 8 | 30 | 0 | 0 | 2 | 2 | 0 | 0 | 1.5 | 1.5 | 3.5 | 3.5
| Sean Walker | 1; 2; 3; 4; 5; 7; 8 | 1; 2; 3; 4 | 1; 2; 3; 4; 5; 7; 8 | 1; 7; 8 | 30 | 0 | 0 | 2.5 | 2.5 | 0 | 0 | 1 | 1 | 3.5 | 3.5
| Shernovius Bennett | 1; 5; 6; 7; 8 | 1; 7; 8 | 1; 5; 6 | 1; 7; 8 | 30 | 0 | 0 | 3 | 3 | 1 | 1 | 3 | 3 | 7 | 7
[5 empty] | Totals | 150 | 0 | 0 | 11.5 | 12 | 1 | 1 | 12.5 | 12.5 | 25 | 25.5
Planned Product Hours < 80% Planned Team Hours.
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| Finalized the design of the User Interface for the mobile applications. Started integrating the UI design for the primary functions (searching for parts, displaying list of search results, etc.). Researched implementing the PayPal SDKs for payments. Created a Management Plan for the cycle. | [6 empty] | Finish incorporating the new UI design into the completed app components. Add ability to delete parts from the MS Access database via the Web API. Add ability to purchase a part if it has a set price and work on incorporating the PayPal SDKs. Finalize how the communication for requesting an additional part will work.
| Obstacles encountered since last status report: | [6 empty] | Notes:
| Having to deal with platform differences between iOS and Android as it relates to general approaches to UI. PayPal integration may not be as straightforward as we anticipated. Some of us had tests this week so we weren't able to meet as many days as planned. | [6 empty] | Added user story assignments for user stories 5 and 6
Risks facing the project:
We are still waiting for their third party developer to move Willie's Cycles' current file-based inventory system over to the new system that will utilize Microsoft Access. Also establishing the software on the local server at Willie's. The firewall configuration will have to be duplicated on their server.

## Member 1 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Ethan Coggin
Week Ending: |  | 2015-03-16
Cycle: |  | Cycle 2
Team Member Work Summary
Monday | Tuesday | Task(s) performed:
Date: | 2015-03-10 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2015-03-11 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | Researched implementing the PayPal SDK for Android
Date: | 2015-03-12 | Result: | Looked into Android PayPal SDK
Hours Worked: | 0.5 | Problems encountered: | Have not decided exactly how we will go about processing payments
Day: | Friday | Task(s) performed:
Date: | 2015-03-13 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-03-14 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | Preparing Status Report for this week
Date: | 2015-03-15 | Result: | Status Report prepared
Hours Worked: | 1 | Problems encountered: | None
Day: | Monday | Task(s) performed: | Preparing Management Plan. Finalizing design of user interface of mobile applications
Date: | 2015-03-16 | Result: | Created list of user story and task assignments for this cycle for Management Plan. Finalized the search and results screen UI
Hours Worked: | 4 | Problems encountered: | None

## Member 2 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | John Boggan
Week Ending: |  | 2015-03-16
Cycle: |  | Cycle 2
Team Member Work Summary
Monday | Tuesday | Task(s) performed: | Translating wireframe mockups into UI design
Date: | 2015-03-10 | Result: | Explored some options for improving the look of the UI
Hours Worked: | 1 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2015-03-11 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-03-12 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-03-13 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-03-14 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | Explored possible design decisions
Date: | 2015-03-15 | Result:
Hours Worked: | 1.5 | Problems encountered:
Day: | Monday | Task(s) performed: | Working on UI design for the iOS application.
Date: | 2015-03-16 | Result: | Hashed out the design for the iOS application. Started integrating design into the app.
Hours Worked: | 3 | Problems encountered:

## Member 3 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Dillon Clary
Week Ending: |  | 2015-03-16
Cycle: |  | Cycle 2
Team Member Work Summary
Monday | Tuesday | Task(s) performed:
Date: | 2015-03-10 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2015-03-11 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-03-12 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-03-13 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-03-14 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-03-15 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed: | Working on UI design
Date: | 2015-03-16 | Result: | Finished main UI
Hours Worked: | 3.5 | Problems encountered:

## Member 4 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Sean Walker
Week Ending: |  | 2015-03-16
Cycle: |  | Cycle 2
Team Member Work Summary
Monday | Tuesday | Task(s) performed:
Date: | 2015-03-10 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2015-03-11 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-03-12 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-03-13 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-03-14 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | Create Gantt Chart for work flow
Date: | 2015-03-15 | Result: | Visual representation of workflow
Hours Worked: | 0.5 | Problems encountered:
Day: | Monday | Task(s) performed: | Meeting about app UI
Date: | 2015-03-16 | Result: | Finished the main UI for the apps
Hours Worked: | 3 | Problems encountered:

## Member 5 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Shernovius Bennett
Week Ending: |  | 2015-03-16
Cycle: |  | Cycle 2
Team Member Work Summary
Monday | Tuesday | Task(s) performed:
Date: | 2015-03-10 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2015-03-11 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | Explore Paypal SDK
Date: | 2015-03-12 | Result: | Determine incorpation isn't as straight forward as aadvertised
Hours Worked: | 3 | Problems encountered: | Finding official SDK
Day: | Friday | Task(s) performed: | Discuss project status with Dan
Date: | 2015-03-13 | Result: | Agree on direction of project
Hours Worked: | 1 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-03-14 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-03-15 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed: | Working on app UI design
Date: | 2015-03-16 | Result: | UI design completed
Hours Worked: | 3 | Problems encountered: