## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Willie's Cycles | [6 empty] | Completed | 1
| Team Members: | Ethan Coggin, John Boggan, Dillon Clary, Sean Walker, Shernovius Bennett | [6 empty] | Discarded | 2
| Date: | 2015-03-23 | Cycle: | 2 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | "Everybody needs a little Willie's" - A mobile application with which users can search for and purchase parts from Willie's Cycles. | [6 empty] | In Review
Unstarted
| Cycle Intent: | Finalize and implement the design of the mobile application user interface. Enable the user to search for and purchase parts with the mobile application.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Search for Parts |  | 1 | 40 | 10 | Adversarial | 6.5 | 25.75
2 | Select a Make |  | 2 | 5 | 3 | Adversarial | 3 | 5.5
3 | Select a Year |  | 2 | 5 | 3 | Adversarial | 3 | 5.5
4 | Select a Part Name |  | 2 | 5 | 3 | Adversarial | 3 | 5.5
5 | Change the Search Year |  | 2 | 5 | 5 | Unstarted | 0 | 0
6 | Clear the Search |  | 2 | 5 | 5 | Collaboration | 1.5 | 1.5
7 | Purchase a Part |  | 2 | 20 | 20 | Collaboration | 2.5 | 2.5
8 | Pay for a Part with PayPal |  | 2 | 20 | 17.5 | Collaboration | 3.5 | 6
9 | Request Additional Information About a Part |  | 2 | 10 | 10 | Unstarted | 0 | 0
10 | View About Us Screen |  | 3 | 5 | 0 | Unstarted | 0 | 0
11 | DISCARDED: Login with Paypal |  | 2 | 15 | 5 | Discarded | 0 | 0
|  |  | Planned Total | 120 | 76.5 | Actual Total | 23 | 52.25

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Willie's Cycles
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Ethan Coggin | 1; 5; 6; 7; 8 | 1; 5; 6; 7; 8 | 2; 3; 4 | 1; 7; 8 | 30 | 0 | 0 | 2 | 6.5 | 0 | 0 | 1.5 | 3 | 3.5 | 9.5
| John Boggan | 1; 2; 3; 4; 6; 7; 8 | 1; 2; 3; 4; 7; 8 | 1; 2; 3; 4; 6 | 1; 7; 8 | 30 | 0 | 0 | 3.5 | 3.5 | 0 | 0 | 11.5 | 14.5 | 15 | 18
| Dillon Clary | 1; 2; 3; 4; 5; 6; 7; 8 | 1; 5; 6 | 7; 8 | 1; 7; 8 | 30 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1.5 | 0 | 3.5
| Sean Walker | 1; 2; 3; 4; 5; 7; 8 | 1; 2; 3; 4 | 1; 2; 3; 4; 5; 7; 8 | 1; 7; 8 | 30 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 1 | 0 | 3.5
| Shernovius Bennett | 1; 5; 6; 7; 8 | 1; 7; 8 | 1; 5; 6 | 1; 7; 8 | 30 | 0 | 0 | 2 | 5 | 1 | 2 | 0 | 3 | 3 | 10
[5 empty] | Totals | 150 | 0 | 0 | 7.5 | 19.5 | 1 | 2 | 13 | 23 | 21.5 | 44.5
Planned Product Hours < 80% Planned Team Hours.
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| Finalized UI design and incorporated final tweeks. Added ability to delete Parts from the database through the Web API. Translated the part name abbreviations into their full names. Finalized how communication between app users and Willie's Cycles's employees will work. Tied up some loose ends with Dan. Incorporated the new UI design into the iOS application. | [6 empty] | Finish incorporating the new UI design into the Android application. Implement table for translating part abbreviations into full part names. Add ability to purchase a part if it has a set price and work on incorporating the PayPal SDKs.
| Obstacles encountered since last status report: | [6 empty] | Notes:
We realized that we would need some way to translate the part name abbreviations (as they appear in the MS Access database) into the full part names that will be displayed in the app. We realized that we needed to make a few more modifications to our backend before everything could be displayed properly.
Risks facing the project:
We are still waiting for their third party developer to move Willie's Cycles' current file-based inventory system over to the new system that will utilize Microsoft Access. Also establishing the software on the local server at Willie's. The firewall configuration will have to be duplicated on their server. There still are not currently real prices for items in their database, and the payment system we are working on setting up is useless if the database items don't have prices.

## Member 1 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Ethan Coggin
Week Ending: |  | 2015-03-23
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | Set up the Status Report for this week
Date: | 2015-03-17 | Result: | Status Report set up and ready to fill out
Hours Worked: | 0.5 | Problems encountered: | None
Day: | Wednesday | Task(s) performed: | Meeting to discuss final tweeks to the UI design, to determine what additional revisions need to be made to the Web API, and to plan the work for the week. Adding ability to delete parts to the Web API.
Date: | 2015-03-18 | Result: | Added ability to delete parts from the database to the Web API.
Hours Worked: | 2.5 | Problems encountered: | None
Day: | Thursday | Task(s) performed:
Date: | 2015-03-19 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-03-20 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-03-21 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-03-22 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed: | Finish putting together Status Report for the week
Date: | 2015-03-23 | Result: | Completed Status Report and emailed to Dr. Chapman
Hours Worked: | 0.5 | Problems encountered: | None

## Member 2 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | John Boggan
Week Ending: |  | 2015-03-23
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | Researching way to improve the look and feel of our UI because one screen with 3 dropdowns is not ideal
Date: | 2015-03-17 | Result: | Found better method of inputting search parameters. Created screen mockups for our final UI design
Hours Worked: | 10 | Problems encountered: | It took a while to find a suitable design approach
Day: | Wednesday | Task(s) performed: | Meeting to plan next steps for this week and the week of Spring Break. Making tweaks to design. Picking a color palette.
Date: | 2015-03-18 | Result: | Figured out what still needs to be done and assigned tasks accordingly. Made changes to design to incorporate any missed functionality
Hours Worked: | 2.5 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-03-19 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed: | Incorporating design mockups into iOS app
Date: | 2015-03-20 | Result: | Existing components of the iOS app are now on the final version of their UI
Hours Worked: | 2.5 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-03-21 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-03-22 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2015-03-23 | Result:
Hours Worked: | 0 | Problems encountered:

## Member 3 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Dillon Clary
Week Ending: |  | 2015-03-23
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Tuesday | Task(s) performed:
Date: | 2015-03-17 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2015-03-18 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-03-19 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-03-20 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-03-21 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-03-22 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2015-03-23 | Result:
Hours Worked: | 0 | Problems encountered:

## Member 4 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Sean Walker
Week Ending: |  | 2015-03-23
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Tuesday | Task(s) performed:
Date: | 2015-03-17 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2015-03-18 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-03-19 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-03-20 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-03-21 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-03-22 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2015-03-23 | Result:
Hours Worked: | 0 | Problems encountered:

## Member 5 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Shernovius Bennett
Week Ending: |  | 2015-03-23
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Tuesday | Task(s) performed:
Date: | 2015-03-17 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Meeting about backend changes
Date: | 2015-03-18 | Result: | Working on translating part abbreviations into full part names
Hours Worked: | 2 | Problems encountered:
Day: | Thursday | Task(s) performed: | Spoke with Dan to confirm a few things
Date: | 2015-03-19 | Result: | Prices will be included in the database. Search will only be by make, year, and part; no optional model
Hours Worked: | 1 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-03-20 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-03-21 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-03-22 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2015-03-23 | Result:
Hours Worked: | 0 | Problems encountered: