## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Willie's Cycles | [6 empty] | Completed | 1
| Team Members: | Ethan Coggin, John Boggan, Dillon Clary, Sean Walker, Shernovius Bennett | [6 empty] | Discarded | 2
| Date: | 2015-04-02 | Cycle: | 2 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | "Everybody needs a little Willie's" - A mobile application with which users can search for and purchase parts from Willie's Cycles. | [6 empty] | In Review
Unstarted
| Cycle Intent: | Finalize and implement the design of the mobile application user interface. Enable the user to search for and purchase parts with the mobile application.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Search for Parts |  | 1 | 40 | 10 | Adversarial | 7.5 | 25.75
2 | Select a Make |  | 2 | 5 | 3 | Adversarial | 5 | 6.5
3 | Select a Year |  | 2 | 5 | 3 | Adversarial | 6 | 7.5
4 | Select a Part Name |  | 2 | 5 | 3 | Adversarial | 6 | 7.5
5 | Change the Search Year |  | 2 | 5 | 5 | Unstarted | 0 | 0
6 | Clear the Search |  | 2 | 5 | 5 | Collaboration | 2.5 | 2.5
7 | Purchase a Part |  | 2 | 20 | 20 | Collaboration | 2.5 | 2.5
8 | Pay for a Part with PayPal |  | 2 | 20 | 17.5 | Collaboration | 4 | 6.5
9 | Request Additional Information About a Part |  | 2 | 10 | 10 | Unstarted | 0 | 0
10 | View About Us Screen |  | 3 | 5 | 0 | Unstarted | 0 | 0
11 | DISCARDED: Login with Paypal |  | 2 | 15 | 5 | Discarded | 0 | 0
|  |  | Planned Total | 120 | 76.5 | Actual Total | 33.5 | 58.75

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Willie's Cycles
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Ethan Coggin | 1; 5; 6; 7; 8 | 1; 5; 6; 7; 8 | 2; 3; 4 | 1; 7; 8 | 30 | 0 | 0 | 5.5 | 12 | 0 | 0 | 2.5 | 5.5 | 8 | 17.5
| John Boggan | 1; 2; 3; 4; 6; 7; 8 | 1; 2; 3; 4; 7; 8 | 1; 2; 3; 4; 6 | 1; 7; 8 | 30 | 0 | 0 | 6.5 | 10 | 0 | 0 | 8 | 22.5 | 14.5 | 32.5
| Dillon Clary | 1; 2; 3; 4; 5; 6; 7; 8 | 1; 5; 6 | 7; 8 | 1; 7; 8 | 30 | 0 | 0 | 5 | 7 | 0 | 0 | 0 | 1.5 | 5 | 8.5
| Sean Walker | 1; 2; 3; 4; 5; 7; 8 | 1; 2; 3; 4 | 1; 2; 3; 4; 5; 7; 8 | 1; 7; 8 | 30 | 0 | 0 | 6 | 8.5 | 0 | 0 | 0 | 1 | 6 | 9.5
| Shernovius Bennett | 1; 5; 6; 7; 8 | 1; 7; 8 | 1; 5; 6 | 1; 7; 8 | 30 | 0 | 0 | 6 | 11 | 5 | 7 | 0 | 3 | 11 | 21
[5 empty] | Totals | 150 | 0 | 0 | 29 | 48.5 | 5 | 7 | 10.5 | 33.5 | 44.5 | 89
Planned Product Hours < 80% Planned Team Hours.
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| Translated the part name abbreviations into their full names. Finished incorporating the new UI design into the iOS application. Added missing functionality to the Web API. Completed the Cycle Report. | [6 empty] | Finish incorporating the new UI design into the Android application. Implement table for translating part abbreviations into full part names. Demo app to Dan at Willie's Cycles.
| Obstacles encountered since last status report: | [6 empty] | Notes:
We realized that we would need some way to translate the part name abbreviations (as they appear in the MS Access database) into the full part names that will be displayed in the app. We realized that we needed to make a few more modifications to our backend before everything could be displayed properly.
Risks facing the project:
We are still waiting for their third party developer to move Willie's Cycles' current file-based inventory system over to the new system that will utilize Microsoft Access. Also establishing the software on the local server at Willie's. The firewall configuration will have to be duplicated on their server. There still are not currently real prices for items in their database, and the payment system we are working on setting up is useless if the database items don't have prices.

## Member 1 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Ethan Coggin
Week Ending: |  | 2015-04-02
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Tuesday | Task(s) performed:
Date: | 2015-03-24 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2015-03-25 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-03-26 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-03-27 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-03-28 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-03-29 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed: | Meeting to work on presentation. Removed white space from part query return. Added API call to return data for year spinner and part name spinner.
Date: | 2015-03-30 | Result: | Finished presentation. Finished adding missing API calls.
Hours Worked: | 3.5 | Problems encountered: | None
Day: | Tuesday | Task(s) performed:
Date: | 2015-03-31 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Working on Cycle Report
Date: | 2015-04-01 | Result: | Completed Cycle Report
Hours Worked: | 4.5 | Problems encountered: | None

## Member 2 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | John Boggan
Week Ending: |  | 2015-04-02
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Tuesday | Task(s) performed:
Date: | 2015-03-24 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2015-03-25 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-03-26 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-03-27 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-03-28 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | Continued to build iOS Client for Willie's Cycles
Date: | 2015-03-29 | Result:
Hours Worked: | 2 | Problems encountered:
Day: | Monday | Task(s) performed: | Continued to build iOS Client for Willie's Cycles / Meeting Prep
Date: | 2015-03-30 | Result:
Hours Worked: | 9 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2015-03-31 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed: | PayPal Research. Working on Cycle Report
Date: | 2015-04-01 | Result:
Hours Worked: | 3.5 | Problems encountered: | Research Xamarin PayPal libs

## Member 3 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Dillon Clary
Week Ending: |  | 2015-04-02
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Tuesday | Task(s) performed:
Date: | 2015-03-24 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2015-03-25 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-03-26 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-03-27 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-03-28 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-03-29 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed: | Preparing Presentation
Date: | 2015-03-30 | Result:
Hours Worked: | 2 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2015-03-31 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Documentation
Date: | 2015-04-01 | Result:
Hours Worked: | 3 | Problems encountered:

## Member 4 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Sean Walker
Week Ending: |  | 2015-04-02
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Tuesday | Task(s) performed:
Date: | 2015-03-24 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2015-03-25 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-03-26 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-03-27 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-03-28 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-03-29 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed: | Cycle presentation
Date: | 2015-03-30 | Result: | Assembled
Hours Worked: | 3 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2015-03-31 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Cycle report
Date: | 2015-04-01 | Result: | Created
Hours Worked: | 3 | Problems encountered:

## Member 5 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Shernovius Bennett
Week Ending: |  | 2015-04-02
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | Discuss paypal sitaution
Date: | 2015-03-24 | Result: | Determine paypal integration may not be an option due to time constraints
Hours Worked: | 1 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2015-03-25 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-03-26 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-03-27 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-03-28 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | More discussions with Dan and Terry about app
Date: | 2015-03-29 | Result: | Determine things required from both parties for completion
Hours Worked: | 1 | Problems encountered:
Day: | Monday | Task(s) performed: | Presentation meeting. Phone call with Dan
Date: | 2015-03-30 | Result:
Hours Worked: | 4 | Problems encountered:
Day: | Tuesday | Task(s) performed: | Phone call with Terry
Date: | 2015-03-31 | Result:
Hours Worked: | 1 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Phone call with Dan about paypal. Cycle Report
Date: | 2015-04-01 | Result:
Hours Worked: | 4 | Problems encountered: