## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Willie's Cycles | [6 empty] | Completed | 1
| Team Members: | Ethan Coggin, John Boggan, Dillon Clary, Sean Walker, Shernovius Bennett | [6 empty] | Discarded | 2
| Date: | 2015-04-06 | Cycle: | 3 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | "Everybody needs a little Willie's" - A mobile application with which users can search for and purchase parts from Willie's Cycles. | [6 empty] | In Review
Unstarted
| Cycle Intent: | Finalize and implement the design of the mobile application user interface. Enable the user to search for and purchase parts with the mobile application.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Search for Parts |  | 1 | 40 | 5 | Adversarial | 3 | 28.75
2 | Select a Make |  | 2 | 5 | 2 | Adversarial | 3 | 9.5
3 | Select a Year |  | 2 | 5 | 2 | Adversarial | 5 | 12.5
4 | Select a Part Name |  | 2 | 5 | 2 | Adversarial | 6.5 | 14
5 | Change the Search Year |  | 2 | 5 | 5 | Unstarted | 0 | 0
6 | Clear the Search |  | 2 | 5 | 2.5 | Collaboration | 1 | 3.5
7 | Purchase a Part |  | 2 | 20 | 17.5 | Collaboration | 0 | 2.5
8 | Pay for a Part with PayPal |  | 2 | 20 | 13.5 | Collaboration | 10 | 16.5
9 | Request Additional Information About a Part |  | 2 | 10 | 10 | Unstarted | 0 | 0
10 | View About Us Screen |  | 3 | 5 | 5 | Collaboration | 4 | 4
11 | DISCARDED: Login with Paypal |  | 2 | 15 | 0 | Discarded | 0 | 0
|  |  | Planned Total | 120 | 64.5 | Actual Total | 32.5 | 91.25

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Willie's Cycles
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Ethan Coggin | 1; 5; 6; 7; 8 | 1; 5; 6; 7; 8 | 2; 3; 4 | 1; 7; 8 | 30 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 2.5 | 2.5 | 3 | 3
| John Boggan | 1; 2; 3; 4; 6; 7; 8 | 1; 2; 3; 4; 7; 8 | 1; 2; 3; 4; 6 | 1; 7; 8 | 30 | 0 | 0 | 0 | 0 | 4 | 4 | 22 | 22 | 26 | 26
| Dillon Clary | 1; 2; 3; 4; 5; 6; 7; 8 | 1; 5; 6 | 7; 8 | 1; 7; 8 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sean Walker | 1; 2; 3; 4; 5; 7; 8 | 1; 2; 3; 4 | 1; 2; 3; 4; 5; 7; 8 | 1; 7; 8 | 30 | 0 | 0 | 1 | 1 | 0 | 0 | 8 | 8 | 9 | 9
| Shernovius Bennett | 1; 5; 6; 7; 8 | 1; 7; 8 | 1; 5; 6 | 1; 7; 8 | 30 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 6 | 6
[5 empty] | Totals | 150 | 0 | 0 | 4.5 | 4.5 | 7 | 7 | 32.5 | 32.5 | 44 | 44
Planned Product Hours < 80% Planned Team Hours.
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| Implemented conversions from abbreviated part names to full user-friendly part names. Met with Willie's Cycles to demo application and discuss desired changes. Helped Willie's Cycles set up their PayPal account. Integrating PayPal into iOS application. Incorporating new UI design into Android application. | [6 empty] | Finish incorporating the new UI design into the Android application. Integrate the PayPal SDK with the Android application. Store transaction information in known location (probably database table). Publish initial release of iOS and Android applications.
| Obstacles encountered since last status report: | [6 empty] | Notes:
| Did not have indie license to build and test Android application with Xamarin. Trouble downloading MS Access and Visual Studio on personal computer | [6 empty] | Tuesday and Wednesday of this week were included on the last Status Report of Cycle 2.
Risks facing the project:
We are still waiting for their third party developer to move Willie's Cycles' current file-based inventory system over to the new system that will utilize Microsoft Access. Also establishing the software on the local server at Willie's. The firewall configuration will have to be duplicated on their server. There still are not currently real prices for items in their database, and the payment system we are working on setting up is useless if the database items don't have prices.

## Member 1 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Ethan Coggin
Week Ending: |  | 2015-04-06
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Thursday | Task(s) performed:
Date: | 2015-04-02 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-04-03 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed: | Set up conversions to translate abbreviated part names into full part names for display to users, and to convert full part names into abbreviations for use with database queries. Set up the Status Report for thsi week.
Date: | 2015-04-04 | Result: | Part names are now being returned as their full translated names. Status Report prepared.
Hours Worked: | 3 | Problems encountered: | None
Day: | Sunday | Task(s) performed:
Date: | 2015-04-05 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2015-04-06 | Result:
Hours Worked: | 0 | Problems encountered:

## Member 2 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | John Boggan
Week Ending: |  | 2015-04-06
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Thursday | Task(s) performed: | Dynamic picker loading, various iOS Client work
Date: | 2015-04-02 | Result:
Hours Worked: | 8 | Problems encountered:
Day: | Friday | Task(s) performed: | Meeting with sponsor. Get design / implementation feedback and various other materials needed for Android/iOS clients
Date: | 2015-04-03 | Result:
Hours Worked: | 2 | Problems encountered:
Day: | Saturday | Task(s) performed: | Continued work on iOS client. Mostly relating to about, photo gallery, and licensure.
Date: | 2015-04-04 | Result:
Hours Worked: | 4 | Problems encountered:
Day: | Sunday | Task(s) performed: | Implemented rudimentary PayPal for iOS
Date: | 2015-04-05 | Result:
Hours Worked: | 7 | Problems encountered:
Day: | Monday | Task(s) performed: | Met with sponsor about PayPal integration. Continued to integrate/test PayPal into the Willie's Cycles iOS app.
Date: | 2015-04-06 | Result:
Hours Worked: | 5 | Problems encountered:

## Member 3 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Dillon Clary
Week Ending: |  | 2015-04-06
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Thursday | Task(s) performed:
Date: | 2015-04-02 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-04-03 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-04-04 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-04-05 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2015-04-06 | Result:
Hours Worked: | 0 | Problems encountered:

## Member 4 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Sean Walker
Week Ending: |  | 2015-04-06
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Thursday | Task(s) performed:
Date: | 2015-04-02 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed: | Researched android animations and decided on architecture
Date: | 2015-04-03 | Result: | Architecture complete
Hours Worked: | 1 | Problems encountered:
Day: | Saturday | Task(s) performed: | Fleshed out Android application with decided UI design
Date: | 2015-04-04 | Result: | Almost complete
Hours Worked: | 5 | Problems encountered: | Did not have indie license to build app adn test
Day: | Sunday | Task(s) performed:
Date: | 2015-04-05 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed: | Continued working on android application
Date: | 2015-04-06 | Result:
Hours Worked: | 3 | Problems encountered:

## Member 5 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Shernovius Bennett
Week Ending: |  | 2015-04-06
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Thursday | Task(s) performed: | Consult with Dan about Paypal issue
Date: | 2015-04-02 | Result: | Agree we should push to keep Paypal
Hours Worked: | 1 | Problems encountered: | Time required to implement Paypal
Day: | Friday | Task(s) performed: | Meet with Dan to Demo app and set up remote access
Date: | 2015-04-03 | Result: | Establish remote access to servers
Hours Worked: | 2 | Problems encountered: | Slow connection hindered confirmation
Day: | Saturday | Task(s) performed:
Date: | 2015-04-04 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | Attempt to add Access and Visual Studio
Date: | 2015-04-05 | Result: | Installation failed due to timeout
Hours Worked: | 2 | Problems encountered: | Slow connection casued timeout
Day: | Monday | Task(s) performed: | Download new version of software
Date: | 2015-04-06 | Result: | New Access downloaded installation pending
Hours Worked: | 1 | Problems encountered: