## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Willie's Cycles | [6 empty] | Completed | 1
| Team Members: | Ethan Coggin, John Boggan, Dillon Clary, Sean Walker, Shernovius Bennett | [6 empty] | Discarded | 2
| Date: | 2015-04-13 | Cycle: | 3 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | "Everybody needs a little Willie's" - A mobile application with which users can search for and purchase parts from Willie's Cycles. | [6 empty] | In Review
Unstarted
| Cycle Intent: | Finalize and implement the design of the mobile application user interface. Enable the user to search for and purchase parts with the mobile application.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Search for Parts |  | 1 | 40 | 5 | Adversarial | 6.5 | 35.25
2 | Select a Make |  | 2 | 5 | 2 | Adversarial | 1 | 10.5
3 | Select a Year |  | 2 | 5 | 2 | Adversarial | 2 | 14.5
4 | Select a Part Name |  | 2 | 5 | 2 | Adversarial | 2.5 | 16.5
5 | Change the Search Year |  | 2 | 5 | 5 | Unstarted | 0 | 0
6 | Clear the Search |  | 2 | 5 | 2.5 | Adversarial | 1 | 4.5
7 | Purchase a Part |  | 2 | 20 | 17.5 | Collaboration | 0 | 2.5
8 | Pay for a Part with PayPal |  | 2 | 20 | 13.5 | Adversarial | 1.5 | 18
9 | Request Additional Information About a Part |  | 2 | 10 | 10 | Unstarted | 0 | 0
10 | View About Us Screen |  | 3 | 5 | 5 | Collaboration | 0 | 4
11 | DISCARDED: Login with Paypal |  | 2 | 15 | 0 | Discarded | 0 | 0
|  |  | Planned Total | 120 | 64.5 | Actual Total | 14.5 | 105.75

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Willie's Cycles
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Ethan Coggin | 1; 5; 6; 7; 8 | 1; 5; 6; 7; 8 | 2; 3; 4 | 1; 7; 8 | 30 | 0 | 0 | 0.5 | 1 | 0 | 0 | 3 | 5.5 | 3.5 | 6.5
| John Boggan | 1; 2; 3; 4; 6; 7; 8 | 1; 2; 3; 4; 7; 8 | 1; 2; 3; 4; 6 | 1; 7; 8 | 30 | 0 | 0 | 0 | 0 | 0 | 4 | 1.5 | 23.5 | 1.5 | 27.5
| Dillon Clary | 1; 2; 3; 4; 5; 6; 7; 8 | 1; 5; 6 | 7; 8 | 1; 7; 8 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sean Walker | 1; 2; 3; 4; 5; 7; 8 | 1; 2; 3; 4 | 1; 2; 3; 4; 5; 7; 8 | 1; 7; 8 | 30 | 2 | 2 | 0 | 1 | 0 | 0 | 8 | 16 | 10 | 19
| Shernovius Bennett | 1; 5; 6; 7; 8 | 1; 7; 8 | 1; 5; 6 | 1; 7; 8 | 30 | 0 | 0 | 0 | 3 | 1 | 4 | 2 | 2 | 3 | 9
[5 empty] | Totals | 150 | 2 | 2 | 0.5 | 5 | 1 | 8 | 14.5 | 47 | 18 | 62
Planned Product Hours < 80% Planned Team Hours.
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| Returning proper model name and part location with parts query. Added back the changes that were accidentally overwritten. Added private key to Web API calls to prevent unauthorized access. Incorporated the new UI design into the Android application and completed the search transitions. | [6 empty] | Finish incorporating the new UI design into the Android application. Integrate the PayPal SDK with the Android application. Store transaction information in known location (probably database table). Publish initial release of iOS and Android applications.
| Obstacles encountered since last status report: | [6 empty] | Notes:
Some of our Web API changes from last time were accidentally overwritten, so those changes had to be added again. Some part names contain the ' character, but that character is illegal for SQL queries so it has to be escaped. Some minor issues with getting the native iOS and Android PayPal SDKs to work with Xamarin.
Risks facing the project:
We still need to establish the software on the local server at Willie's. The firewall configuration will have to be duplicated on their server. There still are not currently real prices for items in their database, and the payment system we are working on setting up is useless if the database items don't have prices.

## Member 1 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Ethan Coggin
Week Ending: |  | 2015-04-13
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | Return split make and model name with parts query. Return part location with parts query. Set up Status Report.
Date: | 2015-04-07 | Result: | Returning correct make and model name and part location with parts query. Added back components of Web API that were accidentally overwritten. Status Report set up and ready to fill out.
Hours Worked: | 2.5 | Problems encountered: | Some of the most recent changes made to the Web API were accidentally overwritten so they had to be re-implemented. The ' character is illegal in SQL queries, so it has to be escaped since some part names contain it.
Day: | Wednesday | Task(s) performed:
Date: | 2015-04-08 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-04-09 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-04-10 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-04-11 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | Added private key to Web API calls to prevent unauthorized access.
Date: | 2015-04-12 | Result: | All Web API calls now require a private key.
Hours Worked: | 1 | Problems encountered: | When using a personally defined return type you can't directly return an Http Response. Can only throw an exception or return an object of the defined return type.
Day: | Monday | Task(s) performed:
Date: | 2015-04-13 | Result:
Hours Worked: | 0 | Problems encountered:

## Member 2 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | John Boggan
Week Ending: |  | 2015-04-13
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | Continued work on testing the iOS PayPal integration.
Date: | 2015-04-07 | Result:
Hours Worked: | 1.5 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2015-04-08 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-04-09 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-04-10 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-04-11 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-04-12 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2015-04-13 | Result:
Hours Worked: | 0 | Problems encountered:

## Member 3 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Dillon Clary
Week Ending: |  | 2015-04-13
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Tuesday | Task(s) performed:
Date: | 2015-04-07 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2015-04-08 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-04-09 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-04-10 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-04-11 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-04-12 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2015-04-13 | Result:
Hours Worked: | 0 | Problems encountered:

## Member 4 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Sean Walker
Week Ending: |  | 2015-04-13
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | Worked on android application
Date: | 2015-04-07 | Result: | Finished fragment transistions
Hours Worked: | 6 | Problems encountered: | Some translation from xamarin to java issues
Day: | Wednesday | Task(s) performed:
Date: | 2015-04-08 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | Continued android application
Date: | 2015-04-09 | Result: | refactored and completed search
Hours Worked: | 4 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-04-10 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-04-11 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-04-12 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2015-04-13 | Result:
Hours Worked: | 0 | Problems encountered:

## Member 5 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Shernovius Bennett
Week Ending: |  | 2015-04-13
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Tuesday | Task(s) performed:
Date: | 2015-04-07 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Meet with Dan to finalize product direction.
Date: | 2015-04-08 | Result: | Agree on product design
Hours Worked: | 1 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-04-09 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-04-10 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-04-11 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-04-12 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed: | Work on server after firewall changes
Date: | 2015-04-13 | Result: | Gain access back to server after adjustments
Hours Worked: | 2 | Problems encountered: