## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Willie's Cycles | [6 empty] | Completed | 1
| Team Members: | Ethan Coggin, John Boggan, Dillon Clary, Sean Walker, Shernovius Bennett | [6 empty] | Discarded | 2
| Date: | 2015-04-20 | Cycle: | 3 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | "Everybody needs a little Willie's" - A mobile application with which users can search for and purchase parts from Willie's Cycles. | [6 empty] | In Review
Unstarted
| Cycle Intent: | Finalize and implement the design of the mobile application user interface. Enable the user to search for and purchase parts with the mobile application.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Search for Parts |  | 1 | 40 | 5 | Adversarial | 12 | 40.75
2 | Select a Make |  | 2 | 5 | 2 | Adversarial | 2 | 11.5
3 | Select a Year |  | 2 | 5 | 2 | Adversarial | 4.25 | 16.75
4 | Select a Part Name |  | 2 | 5 | 2 | Adversarial | 4.75 | 18.75
5 | Change the Search Year |  | 2 | 5 | 5 | Unstarted | 0 | 0
6 | Clear the Search |  | 2 | 5 | 2.5 | Adversarial | 2 | 5.5
7 | Purchase a Part |  | 2 | 20 | 17.5 | Collaboration | 2.5 | 5
8 | Pay for a Part with PayPal |  | 2 | 20 | 13.5 | Adversarial | 8.5 | 25
9 | Request Additional Information About a Part |  | 2 | 10 | 10 | Adversarial | 2 | 2
10 | View About Us Screen |  | 3 | 5 | 5 | Collaboration | 0 | 4
11 | DISCARDED: Login with Paypal |  | 2 | 15 | 0 | Discarded | 0 | 0
|  |  | Planned Total | 120 | 64.5 | Actual Total | 38 | 129.25

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Willie's Cycles
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Ethan Coggin | 1; 5; 6; 7; 8 | 1; 5; 6; 7; 8 | 2; 3; 4 | 1; 7; 8 | 30 | 0 | 0 | 1 | 2 | 0 | 0 | 3.5 | 9 | 4.5 | 11
| John Boggan | 1; 2; 3; 4; 6; 7; 8 | 1; 2; 3; 4; 7; 8 | 1; 2; 3; 4; 6 | 1; 7; 8 | 30 | 0 | 0 | 0 | 0 | 0 | 4 | 7 | 33.5 | 7 | 37.5
| Dillon Clary | 1; 2; 3; 4; 5; 6; 7; 8 | 1; 5; 6 | 7; 8 | 1; 7; 8 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sean Walker | 1; 2; 3; 4; 5; 7; 8 | 1; 2; 3; 4 | 1; 2; 3; 4; 5; 7; 8 | 1; 7; 8 | 30 | 0 | 2 | 0 | 1 | 0 | 0 | 8 | 24 | 8 | 27
| Shernovius Bennett | 1; 5; 6; 7; 8 | 1; 7; 8 | 1; 5; 6 | 1; 7; 8 | 30 | 0 | 0 | 0 | 3 | 2.5 | 6.5 | 5 | 7 | 7.5 | 16.5
[5 empty] | Totals | 150 | 0 | 2 | 1 | 6 | 2.5 | 10.5 | 23.5 | 73.5 | 27 | 92
Planned Product Hours < 80% Planned Team Hours.
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| Finished incorporating the new UI design into the Android application. Completed the majority of the tests for our Web API. Fixed issues that arose with PayPal on iOS due to 64-bit compatiblity issues, PayPal completed on iOS. | [6 empty] | Integrate the PayPal SDK with the Android application. Complete transaction table. Complete testing suite for PayPal. Establish software on local server at Willie's. Publish iOS and Android applications.
| Obstacles encountered since last status report: | [6 empty] | Notes:
There were some bugs in the PayPal iOS SDK that were causing issues with 64-bit versions of iOS. Issues with installing software on Willie's Cycles's server.
Risks facing the project:
We still need to establish the software on the local server at Willie's. The firewall configuration will have to be duplicated on their server.

## Member 1 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Ethan Coggin
Week Ending: |  | 2015-04-20
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | Working on Web API method for inserting transation information into database. Set up our testing infrastructure for our Web API. Set up Status Report
Date: | 2015-04-14 | Result: | Set up as much of the insertion API as I could up to this point. Web API testing infrastructure prepared. Status Report prepared and ready to be filled out.
Hours Worked: | 3 | Problems encountered: | Pierce ran into issues with PayPal iOS SDK, so having to wait on him to get a list of the transaction information available from PayPal.
Day: | Wednesday | Task(s) performed:
Date: | 2015-04-15 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-04-16 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-04-17 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-04-18 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-04-19 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed: | Working on tests for Web API. Preparing Status Report for submission.
Date: | 2015-04-20 | Result: | Completed tests for majority of Web API. Status Report prepared and submitted.
Hours Worked: | 1.5 | Problems encountered: | None

## Member 2 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | John Boggan
Week Ending: |  | 2015-04-20
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | Sort out some PayPal bugs (64-bit issues)
Date: | 2015-04-14 | Result:
Hours Worked: | 3 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2015-04-15 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | Continue work on trying to solve the PayPal issue.
Date: | 2015-04-16 | Result:
Hours Worked: | 3 | Problems encountered:
Day: | Friday | Task(s) performed: | Continue work on trying to solve the PayPal issue. Working with PayPal support.
Date: | 2015-04-17 | Result:
Hours Worked: | 1 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-04-18 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-04-19 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2015-04-20 | Result:
Hours Worked: | 0 | Problems encountered:

## Member 3 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Dillon Clary
Week Ending: |  | 2015-04-20
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Tuesday | Task(s) performed:
Date: | 2015-04-14 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2015-04-15 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-04-16 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-04-17 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-04-18 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-04-19 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2015-04-20 | Result:
Hours Worked: | 0 | Problems encountered:

## Member 4 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Sean Walker
Week Ending: |  | 2015-04-20
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | List adapters
Date: | 2015-04-14 | Result:
Hours Worked: | 3 | Problems encountered: | Some xamarin layouts vary from native android
Day: | Wednesday | Task(s) performed: | Dialog fragment
Date: | 2015-04-15 | Result:
Hours Worked: | 3 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2015-04-16 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2015-04-17 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-04-18 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2015-04-19 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed: | Wire up email and work on paypal
Date: | 2015-04-20 | Result:
Hours Worked: | 2 | Problems encountered:

## Member 5 Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Willie's Cycles
Member: |  | Shernovius Bennett
Week Ending: |  | 2015-04-20
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Tuesday | Task(s) performed: | Attempt to install Access 2013
Date: | 2015-04-14 | Result: | Failure
Hours Worked: | 2 | Problems encountered: | Can't install w/ remote access
Day: | Wednesday | Task(s) performed:
Date: | 2015-04-15 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | Search for work around to slove installation issue
Date: | 2015-04-16 | Result: | Failure
Hours Worked: | 1 | Problems encountered: | RDP must be removed to install
Day: | Friday | Task(s) performed: | Install Access and connectivity component onsite
Date: | 2015-04-17 | Result: | installation complete
Hours Worked: | 2 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2015-04-18 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | Meet with Dan for status update
Date: | 2015-04-19 | Result:
Hours Worked: | 2.5 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2015-04-20 | Result:
Hours Worked: | 0 | Problems encountered: